## Sheet1
Risk ID | Problem | Priority | Prob | Cost | EMV
R1 | Project Team Members resigning | High | 0.15 | 5000 | 750
R2 | New Store Location | Low | 0.3 | 3500 | 1050
R3 | New Store Setup Cost | Low | 0.25 | 4000 | 1000
R4 | Private Network Failure | High | 0.45 | 10000 | 4500
R5 | Store Manager Workload | Medium | 0.75 | 2000 | 1500
R6 | IT Resource Unavailability | High | 0.35 | 5000 | 1750
R7 | Over-dependency in Outsourcing | Low | 0.25 | 1500 | 375
R8 | Slack in Schedule | High | 0.8 | 40000 | 32000
R9 | Complex Activity Dependency | Medium | 0.25 | 7000 | 1750
R10 | Timely Availability of Resources | High | 0.45 | 10000 | 4500
R11 | Work duty documentation | Low | 0.05 | 2000 | 100
R12 | Activity Monitoring | Low | 0.25 | 3000 | 750
R13 | Dimension and Version Incompatibility | Low | 0.05 | 10000 | 500
R14 | Scope Creep | Low | 0.15 | 50000 | 7500
[5 empty] | 58025 | Add this to contengency